## Sheet1
Req ID | Requirement Title | Description | Business Form | Req Source | Type | Category | Module | Size | Difficulty | Key | Priority | PIC | Estimate(hour) | Coding Effort(pd) | Status | Change Status Date
F001 | Create & Insert Database | [9 empty] | Critical | Anh Khoa | 10 |  | Done
F002 | Sign Up Form | [9 empty] | High | Châu Phát | 5 |  | TO DO
F003 | Sign In Form | [9 empty] | High | Trọng Lễ | 4 |  | TO DO
F004 | Forget Password & Change Password | [9 empty] | Medium | Thanh Tài | 12 |  | TO DO
F005 | Load All Products | [9 empty] | High | Tấn Lộc | 3 |  | TO DO
F006 | Load Product's detail | [9 empty] | Medium | Tấn Lộc | 4 |  | TO DO
F007 | Admin UI, Login | [9 empty] | High | Hồ Phát | 8 |  | Done
F008 | Admin's Access, Function | [9 empty] | Medium | Trọng Lễ | 6 |  | TO DO